## Project Gantt Chart
Task | Start Date | End Date
Setup & Boilerplate | 2025-07-15 | 2025-07-19
Identity Module | 2025-07-20 | 2025-07-30
Catalog Module | 2025-07-31 | 2025-08-10
Ordering Module | 2025-08-11 | 2025-08-23
Polish & Testing | 2025-08-24 | 2025-08-29
GitHub Actions | 2025-07-31 | 2025-08-04

## Risk & Changes
Feature | Estimated Hours | Estimated Days | Notes
Token Cancellation Feature | 10 | 5 | Requires endpoint revocation logic.
Distributed Transaction Rollback | 16 | 8 | Implement Outbox or Saga pattern.